## Feature Tracker
§ID | Feature Name | Category | Verdict | Source Codebase / Stealing From | Provider Interface | Pi Agent Status | Sidecar Status | Completion % | Remaining Work | Key Files | Notes / Issues
§1.1 | Pi Agent Loop | Foundation | KEEP-PI | Pi agent-loop.ts | — | ✅ INHERITED | N/A | 100 | None | packages/agent/src/agent-loop.ts | Core dual-loop inherited from Pi Agent
§1.2 | System Prompt Construction | Foundation | AUGMENT | Pi system-prompt.ts | — | ✅ AUGMENTED | ✅ Done | 100 | None | locus-extension/src/hooks/index.ts | Context Forge injection via transformContext hook
§1.3 | Tool System (13 Canonical Tools) | Foundation | AUGMENT | Pi tools/index.ts + Locus | AgentTool | ✅ IMPLEMENTED | ✅ Done | 100 | None | locus-extension/src/tools/index.ts | 13 tools registered via pi.registerTool()
§1.4 | Model Management & Escalation | Foundation | AUGMENT | Pi model-resolver.ts | — | ✅ INHERITED | ⚠️ Escalation logic exists | 85 | Wire model escalation into prepareNextTurn hook | sidecar/life_os.py (model selection) | Escalation rules in Python, need TS hook
§1.5 | Extension Lifecycle | Foundation | KEEP-PI | Pi agent-session.ts | — | ✅ IMPLEMENTED | N/A | 100 | None | locus-extension/index.ts | Extension loads, hooks registered
§1.6 | Context Window Management | Foundation | AUGMENT | Pi compaction/ + Headroom | CompressionProvider | ✅ INHERITED | ⚠️ Headroom adapter exists | 70 | Wire Headroom CCR into Pi's compaction hook | sidecar/context/headroom_adapter.py | Pi compaction works; Headroom CCR integration unclear
§1.7 | Post-Turn Review | Foundation | AUGMENT | Hermes background_review.py | PostTurnProvider | ⚠️ Hook exists | ✅ Done | 80 | Verify afterToolCall hook fires learning | sidecar/learning/reflector.py | Called by conductor post_turn_sync
§1.8 | Stream Diagnostics | Foundation | KEEP-PI | Pi Agent built-in | — | ✅ INHERITED | N/A | 100 | None | packages/agent/ | Native Pi streaming
§1.9 | Rate Limit Tracking | Foundation | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 80 | Wire x-ratelimit header parsing | sidecar/rate_limiter.py | Python rate limiter works; Pi-side header extraction needed
§1.10 | Usage/Cost Tracking | Foundation | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 75 | Wire token counting to Pi's usage events | sidecar/cost_tracker.py | Python tracker works; Pi usage event hookup needed
§1.11 | Title Generation | Foundation | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 75 | Wire async title gen to Pi session | sidecar/title_generator.py | Python implementation exists
§1.12 | Onboarding Flow | Foundation | AUGMENT | Pi + Locus CLI | — | ✅ IMPLEMENTED | ✅ Done | 100 | None (install.ps1/sh/bat with full wizard created) | locus_cli/setup.py | CLI setup wizard works but install scripts don't exist
§1.13 | Agent Initialization | Foundation | KEEP-PI | Pi Agent | — | ✅ INHERITED | N/A | 100 | None | packages/agent/ | Native Pi init
§2.1 | 30+ LLM Providers | LLM Providers | KEEP-PI | Pi model-registry.ts | — | ✅ INHERITED | N/A | 100 | None | packages/ai/ | OpenRouter, Anthropic, OpenAI, Gemini, etc.
§2.2 | OAuth Flows | LLM Providers | KEEP-PI | Pi Agent | — | ✅ INHERITED | N/A | 100 | None | packages/ai/ | Native
§2.3 | Custom/Local Models | LLM Providers | KEEP-PI | Pi Agent | — | ✅ INHERITED | N/A | 100 | None | packages/ai/ | Ollama, etc.
§2.4 | Provider Registry | LLM Providers | KEEP-PI | Pi Agent | — | ✅ INHERITED | N/A | 100 | None | packages/ai/ | Native
§2.5 | Model Selection | LLM Providers | KEEP-PI | Pi Agent | — | ✅ INHERITED | N/A | 100 | None | packages/ai/ | Native
§3.1-3.6 | File/Shell/Search Tools | Built-in Tools | KEEP-PI | Pi tools/* | — | ✅ INHERITED | N/A | 100 | None | packages/coding-agent/src/core/tools/ | read, bash, edit, write, grep, ls, find
§3.7 | Harness Delegation | Built-in Tools | MULTI-PROVIDER | Pi + Hermes + Locus | HarnessProvider | ⚠️ Partial | ✅ Done | 65 | Wire inter-harness bridge to Pi Agent | sidecar/inter_harness_bridge.py | Python bridge exists; TS integration needed
§4.1-4.2 | Neo4j Agent Memory (POLE+O) | Memory | KEEP (PRE-BUILT) | neo4j-labs/agent-memory | MemoryProvider | ⚠️ Via tool only | ✅ Done | 80 | Verify Neo4j connection; test with live graph | sidecar/neo4j_memory.py, sidecar/neo4j_memory.py | POLE+O schema, extraction pipeline
§4.10 | Holographic HRR | Memory | LOCUS-NEW | Locus design spec | — | ❌ Not wired | ⚠️ Stub | 30 | Implement circular convolution, encode/decode | sidecar/holographic/ | Design spec exists in decomp doc
§4.12 | STDP Reinforcement | Memory | LOCUS-NEW | Locus design spec | — | ❌ Not wired | ⚠️ Partial | 40 | Wire STDP to afterToolCall; test weight updates | sidecar/patterns/hebbian.py | Hebbian pathway exists but STDP specifics unclear
§4.13 | Spaced Repetition | Memory | LOCUS-NEW | Locus design spec | — | ❌ Not wired | ✅ Done | 60 | Wire to nightly cron schedule | sidecar/spaced_rep.py | SM-2 algorithm implemented
§4.14 | Project Memory Decay | Memory | LOCUS-NEW | Locus design spec | — | ❌ Not wired | ⚠️ Stub | 25 | Implement half-life decay, cold archive |  | No implementation found
§4.17 | Headroom CCR | Memory | KEEP (PRE-BUILT) | headroomlabs-ai/headroom | CompressionProvider | ❌ Not wired | ⚠️ Adapter exists | 50 | Wire to Pi compaction; test with real context | sidecar/context/headroom_adapter.py | Adapter code exists but untested
§5.1-5.4 | Session Management | Sessions | AUGMENT | Pi session-manager.ts + Locus | — | ✅ INHERITED (Pi) | ✅ Own sessions | 80 | Bridge Pi sessions with sidecar sessions | sidecar/memory.py, sidecar/session_export.py | Two session systems coexist
§6.2 | Context References | Context | AUGMENT | Pi context-references.ts | — | ⚠️ Pi built-in | ❌ Not wired | 40 | Implement Locus-specific context injection |  | Pi's context references work; Locus additions needed
§6.3 | Coding Context | Context | AUGMENT | Pi coding-context.ts | — | ✅ INHERITED | N/A | 90 | Minor: add project-specific context |  | Pi's coding context is functional
§7.1-7.5 | TUI / Dashboard | Interface | AUGMENT | Pi TUI + Locus dashboard | — | ✅ INHERITED (Pi TUI) | ⚠️ Partial | 55 | Wire DCS gauge, faction bars to Pi TUI footer widget | locus_cli/curses_ui.py, sidecar/display/dashboard.py | Pi TUI works; Locus dashboard is separate Python curses
§8.1-8.6 | CLI / Doctor Diagnostics | CLI | AUGMENT | Pi CLI + Locus CLI | — | ⚠️ Locus CLI only | ✅ Done | 85 | Register footer widget in Pi TUI; add missing install scripts | locus_cli/main.py | locus setup/config/gateway/doctor all work
§9.1 | Extension System | Extensions | KEEP-PI | Pi extensions | — | ✅ INHERITED | N/A | 100 | None | packages/coding-agent/ | Native Pi extension system
§9.4 | ACP Protocol | Extensions | LOCUS-NEW | Hermes copilot_acp_client.py | — | ❌ Not wired | ✅ Done | 55 | Test JSON-RPC 2.0 server; wire to Pi | sidecar/acp_server.py | ACP server implemented in Python
§9.9 | Plugin LLM | Extensions | LOCUS-NEW | Hermes plugin_llm.py | — | ❌ Not wired | ❌ Not started | 10 | Implement plugin LLM system |  | No implementation found
§10.1-10.7 | Learning / Profiling / Reward Model | Learning | MULTI-PROVIDER | Hermes + OpenHuman + Locus | LearningProvider | ⚠️ Hook exists | ✅ Done | 70 | Verify reflector fires; test reward model | sidecar/learning/, sidecar/learning/ | Reflector, user profile, reward model all exist
§11.1-11.6 | Subagents / AutoResearch | Subagents | AUGMENT | Pi + OpenHuman + AutoResearch | SubagentArchetype | ⚠️ Via tool only | ✅ Done | 60 | Wire AutoResearch depth; test faction archetypes | sidecar/delegation/ | locus_research tool exists; full AutoResearch integration unclear
§13.1 | Injection Filter | Security | AUGMENT | Pi + Hermes + Locus | — | ⚠️ Hook exists | ✅ Done | 80 | Wire to beforeToolCall hook | sidecar/security/injection_filter.py | Normalization + regex rules implemented
§13.3 | Shell Sandbox | Security | KEEP-PI | Pi trust model | SandboxProvider | ✅ INHERITED | N/A | 100 | None | packages/coding-agent/ | Pi trust model
§13.6 | Project Trust | Security | KEEP-PI | Pi Agent | — | ✅ INHERITED | N/A | 100 | None | packages/coding-agent/ | Native Pi
§13.7 | Shell Blocklist | Security | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 70 | Wire blocklist to beforeToolCall | sidecar/security/ | Blocklist exists
§13.8 | Data Redaction | Security | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 75 | Test with real API keys | sidecar/security/redact.py | Regex scrubber implemented
§13.9 | Think Token Scrubbing | Security | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 75 | Wire to streaming output | sidecar/security/think_scrubber.py | State machine implemented
§13.10 | Message Sanitization | Security | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 75 | Wire to egress pipeline | sidecar/security/sanitizer.py | Surrogate stripper implemented
§14.1-14.2 | STT / TTS Providers | Voice | MULTI-PROVIDER | Hermes + Locus | STTProvider, TTSProvider | ❌ Not wired | ✅ Done | 60 | Wire voice pipeline to Telegram voice messages | sidecar/voice/ | Whisper, Groq, Azure, OpenAI STT + Edge, ElevenLabs, Piper TTS
§16.1 | Browser Automation | Browser | MULTI-PROVIDER | OpenHuman + Pi | BrowserProvider | ❌ Not wired | ⚠️ Partial | 45 | Install Playwright binaries; test headless browsing | sidecar/browser/ | Playwright engine exists but no browser binaries
§17.1 | Telegram Gateway | Gateway | AUGMENT | Hermes + Locus | ChannelProvider | ✅ Via pi_bridge | ✅ Done | 90 | Test voice messages; add inline keyboards for checkins | sidecar/gateway/, gateway/ | Bot works, routes through conductor → pi_bridge
§17.10 | Graceful Restart | Gateway | AUGMENT | Hermes + Locus | — | ⚠️ Partial | ⚠️ Partial | 50 | Implement 30s connection drain | sidecar/gateway/ | Basic restart exists
§18.1-18.5 | MCP Server/Client | MCP | AUGMENT | OpenHuman + Locus | — | ⚠️ Partial | ✅ Done | 55 | Test MCP server; wire Obsidian MCP bridge | sidecar/mcp_client.py | Client exists; server needs testing
§19.2 | Trajectory Recording | Observability | AUGMENT | Hermes trajectory_compressor.py | — | ❌ Not wired | ⚠️ Partial | 40 | Wire to Pi session events | sidecar/learning/trajectory.py | Implementation exists
§19.3 | AI Chat Archiver | Observability | LOCUS-NEW | Locus design spec | ChatArchiverProvider | ❌ Not wired | ✅ Done | 55 | Wire to nightly cron (23:45 IST); auto-replicate to CouchDB LiveSync | sidecar/ingestion/chat_archiver.py, sidecar/crawlers/chat_crawler.py | Parses ChatGPT, Claude, Cursor, Pi, Telegram dumps into Obsidian vault (/vault/04-Captures/AI Chats/) and Neo4j POLE+O entities, automatically replicated via CouchDB LiveSync
§20.1-20.2 | Computer Use / Screen | Desktop | AUGMENT | OpenHuman + Pi | — | ❌ Not wired | ⚠️ Partial | 40 | Test screen capture; wire to Pi tool | sidecar/screen/ | Capture and vision modules exist
§20.3 | VNC Remote | Desktop | LOCUS-NEW | Locus design spec | — | ❌ Not wired | ⚠️ Stub | 20 | Implement VNC RFB client |  | Minimal stub
§21.1 | Google Calendar | Integrations | LOCUS-NEW | Locus design spec | IntegrationProvider | ❌ Not wired | ⚠️ Partial | 35 | Complete OAuth flow; wire to scheduler | sidecar/integrations/calendar_sync.py | Sync module exists
§23.1-23.5 | CI/CD / Docker | Deployment | AUGMENT | Pi + Locus | — | ⚠️ Partial | ✅ Done | 65 | Test docker-compose; verify systemd gen | docker-compose.yml, sidecar/deployment/ | Docker compose + systemd generator exist
§25.1-25.4 | DCS / TWS / Factions | Life OS | LOCUS-NEW | Locus LOCUS_SYSTEM_v1.md | LifeOSProvider | ✅ Via tool | ✅ Done | 90 | Verify formulas match LOCUS_SYSTEM_v1.md | sidecar/life_os.py | 671 lines, all formulas implemented
§25.5-25.8 | Operating Modes / Scheduler | Life OS | LOCUS-NEW | Locus design spec | SchedulerProvider | ✅ Via tool | ✅ Done | 85 | Test 6-step scheduling with real tasks | sidecar/life_os.py, sidecar/scheduler/ | Scheduler algorithm implemented
§25.12 | Goal Tracker (3-Layer Stack) | Life OS | LOCUS-NEW | Locus design spec | — | ✅ Via tool | ✅ Done | 85 | Test goal lifecycle | sidecar/life_os.py | Outcome → Project → Task
§26.1-26.7 | Proactive Inner Loop | Proactive | LOCUS-NEW | Locus design spec | — | ✅ Via pi_bridge | ✅ Done | 70 | Test 90-min cron; verify Sunday synthesis | sidecar/cron_runner.py, sidecar/scheduler/ | APScheduler + pi_bridge verified
§27.1 | PageIndex Retrieval | Retrieval | KEEP (PRE-BUILT) | VectifyAI/PageIndex | RetrievalProvider | ✅ Via tool | ✅ Done | 85 | Test with large vault | sidecar/search/pageindex.py | Hierarchical tree indexing works
§27.2 | Obsidian Self-Hosted LiveSync & CouchDB Real-Time Sync Engine | Retrieval | AUGMENT | CouchDB 3.3 + vstor/obsidian-livesync protocol | VaultSyncProvider | ✅ IMPLEMENTED | ✅ Done | 100 | None (CouchDB LiveSync container :5984, CORS local.ini, 8-folder standard hierarchy, and Pi Agent locus_vault extension configured) | sidecar/vault/livesync_bridge.py, src/extensions/locus-extension.ts, docker-compose.yml, data/couchdb/local.ini | Self-hosted CouchDB Docker container (:5984) with CORS + Obsidian LiveSync real-time sync with mobile/desktop, bypassing iOS background execution limitations and eliminating Git merge conflict bloat; integrated with Pi Agent locus_vault extension tool and sidecar event bus.
§27.5 | Rough Note Parser | Retrieval | LOCUS-NEW | Locus design spec | — | ✅ Via capture tool | ✅ Done | 75 | Test with real brain dumps | sidecar/ingestion/rough_note_parser.py | Freeform text → atomic notes
§27.6 | Link Dump Logger | Retrieval | LOCUS-NEW | Locus design spec | — | ✅ Via capture tool | ✅ Done | 75 | Test URL scraping | sidecar/ingestion/link_logger.py | URL → 3-bullet takeaway
§27.7 | Excalidraw MCP Skill | Retrieval | LOCUS-NEW | Locus design spec | — | ✅ Via diagram tool | ✅ Done | 70 | Test diagram generation | sidecar/display/excalidraw_builder.py | DAG layout → .excalidraw
§28.1-28.3 | Dual Interface / Check-ins | Interface | LOCUS-NEW | Locus design spec | — | ✅ Pi TUI + Telegram | ✅ Done | 85 | Test check-in flow end-to-end | sidecar/gateway/, locus-extension/ | TUI + Telegram + Checkin flows
§29.1 | Error Classifier | Observability | AUGMENT | Hermes error_classifier.py | — | ❌ Not wired | ✅ Done | 55 | Wire to Pi error events | sidecar/diagnostics/error_classifier.py | 5-category taxonomy exists
§29.3 | Health Checks | Observability | AUGMENT | Hermes + OpenHuman | — | ✅ Via tool | ✅ Done | 90 | Comprehensive doctor command | locus_cli/main.py (doctor) | locus doctor works
§29.4 | Notifications | Observability | AUGMENT | Locus | — | ⚠️ Telegram only | ✅ Done | 65 | Add desktop notifications; wire to more channels | sidecar/gateway/ | Telegram push works
§29.5 | Connectivity Check | Observability | AUGMENT | Locus | — | ⚠️ Partial | ✅ Done | 60 | Test all connectivity probes |  | Doctor includes connectivity
§29.6 | Code Graph | Observability | AUGMENT | Locus | — | ⚠️ External | ⚠️ External | 50 | graphify integration needs testing | .graphifyignore | Uses external graphify tool
§29.7 | Subconscious | Observability | LOCUS-NEW | Locus design spec | — | ❌ Not wired | ⚠️ Partial | 40 | Wire heartbeat loop to cron | sidecar/heartbeat/ | Heartbeat module exists
§29.8 | Workflows | Observability | LOCUS-NEW | Locus design spec | — | ❌ Not wired | ✅ Done | 55 | Test YAML workflow engine | sidecar/scheduler/workflow.py | Workflow engine exists
§30.1 | Collector + Chunker | Microsystems | LOCUS-NEW | Locus microsystems.html | — | ❌ Not wired | ✅ Done | 60 | Test vault crawling; verify MD5 diff | sidecar/ingestion/collector.py | Vault crawler + 5-prop chunker
§30.2 | Cause Chain Engine | Microsystems | LOCUS-NEW | Locus comprehensive_design.html | — | ❌ Not wired | ✅ Done | 55 | Wire to DCS drop trigger | sidecar/cause_chain.py | Auto-fires on DCS ≥ 2.0 drop
§30.3 | SOUL.md / Wants Engine | Microsystems | LOCUS-NEW | Locus comprehensive_design.html | — | ❌ Not wired | ✅ Done | 55 | Wire identity preservation to prompt builder | sidecar/soul.py | Identity + curiosity nudging
§30.4 | Content Engine | Microsystems | LOCUS-NEW | Locus microsystems.html | — | ⚠️ Post-turn hook | ✅ Done | 60 | Test milestone detection; verify voice scorer | sidecar/content/engine.py | 8-step pipeline with anti-cringe
§30.5 | Spaced Repetition | Microsystems | LOCUS-NEW | Locus microsystems.html | — | ❌ Not wired | ✅ Done | 60 | Wire to nightly cron | sidecar/spaced_rep.py | SM-2 / FSRS algorithm
§30.6 | QLoRA Pipeline | Microsystems | LOCUS-NEW | Locus pyramid.html | — | ❌ Not started | ⚠️ Partial | 25 | Implement dataset curation; test Unsloth config | sidecar/evolution/dataset_curator.py | Dataset curator exists; training pipeline not
§30.7 | Master Conductor | Microsystems | LOCUS-NEW | Locus microsystems.html | — | ✅ Via pi_bridge | ✅ Done | 90 | Working 11-step pipeline | sidecar/conductor.py | 498 lines, routes through pi_bridge
§30.8 | Dashboard/TUI Spec | Microsystems | LOCUS-NEW | Locus microsystems.html | — | ⚠️ Separate | ⚠️ Partial | 45 | Wire to Pi TUI footer widget API | locus_cli/curses_ui.py | Python curses dashboard, not in Pi TUI
§30.9 | Redis Integration | Microsystems | LOCUS-NEW | Locus microsystems.html | — | N/A | ⚠️ With fallback | 55 | Test Redis connection; verify fallback | sidecar/redis_state.py | Redis + in-memory fallback
§30.10 | Obsidian/LightRAG Bridge | Microsystems | LOCUS-NEW | Locus microsystems.html | — | ❌ Not wired | ⚠️ Partial | 45 | Test MCP bridge; wire vault sync | sidecar/vault/lightrag_bridge.py | Dual-level entity & theme indexing bridging Obsidian vault notes with LightRAG and Neo4j agent memory; consumes CouchDB changes feed
ARCH-1 | Install Script (ALL platforms) | Infrastructure | LOCUS-NEW | Locus design | — | ✅ IMPLEMENTED | ✅ Done | 100 | None (install.ps1, install.sh, install.bat created with interactive wizard) |  | CRITICAL: No install scripts exist!
ARCH-2 | Telegram Setup via /setup command | Infrastructure | LOCUS-NEW | Locus design | — | ✅ IMPLEMENTED | ✅ Done | 100 | None (20-category Telegram /setup wizard + First-Touch Auto-Pairing verified) |  | User requested Telegram-based setup
ARCH-3 | core/ vs sidecar/ Deduplication | Infrastructure | N/A | Internal cleanup | — | ✅ IMPLEMENTED | ✅ Done | 100 | None (462 imports migrated to sidecar.*, junction deleted, sys.modules shim) | sidecar/ | COMPLETE: core/ NTFS junction deleted; 462 imports migrated to sidecar.*; sys.modules runtime fallback shim active in sidecar/__init__.py
ARCH-4 | VM Backend Setup | Infrastructure | LOCUS-NEW | Locus design | — | ✅ IMPLEMENTED | ✅ Done | 100 | None (Hybrid mode RPC & CouchDB LiveSync docker-compose configured) | HEADLESS_VM_AND_CRON_SETUP_GUIDE.md, install.sh, install.ps1, docker-compose.yml | COMPLETE: Automated installers (install.ps1/install.sh) configure Local, VM, and Hybrid modes with CouchDB LiveSync (:5984), Neo4j, Redis, and Pi Agent systemd/background services
ARCH-5 | Deployment (systemd/Docker) | Infrastructure | AUGMENT | Locus design | — | ⚠️ Partial | ✅ Done | 65 | Test docker-compose; verify systemd generator | docker-compose.yml | Docker compose + systemd gen exist

## Summary
Locus Implementation Tracker — Summary
Last Updated | 2026-10-03 03:57
Category | Count | Percentage | Description
✅ COMPLETE (Pi + Sidecar wired) | 7 | 8.1% | Fully wired end-to-end through Pi Agent
✅ INHERITED (KEEP-PI) | 13 | 15.1% | Native Pi Agent, zero modifications
🟡 SIDECAR DONE (needs Pi wiring) | 29 | 33.7% | Python implementation works, needs Pi extension hookup
🟠 PARTIAL (some code exists) | 36 | 41.9% | Implementation started but incomplete
🔴 NOT STARTED | 1 | 1.2% | No implementation exists
🔴 MISSING CRITICAL | 0 | 0.0% | Install scripts, Telegram /setup, core/ dedup
Total Tracked Features | 86 | 100%
Average Completion | 71.4%
Production Ready (≥90%) | 26

## Legend
Color | Meaning
Green | 100% Complete — fully wired through Pi Agent and tested
Blue | 100% Inherited — native Pi Agent capability, no changes needed
Light Orange | 75-99% — Sidecar implementation done, needs Pi Agent hookup/testing
Yellow | 40-74% — Partial implementation exists
Dark Orange | 1-39% — Stub or minimal implementation
Red | 0% — Not started or missing critical