## Feature Tracker
ID | Spec section(s) | Feature | Category | Verdict | Source Codebase / Stealing From | Provider Interface | Layer | Verified Level | Verified % | Claimed % (old tracker, unverified) | Claim minus Evidence | Remaining Work (derived) | Flags | Evidence Files | Why Not Higher
F-0001 | §1.1: Pi Agent Loop (Foundation) | Pi Agent Loop | Foundation | KEEP-PI | Pi agent-loop.ts |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/agent/src/agent-loop.ts
F-0002 | §1.2: System Prompt Construction | System Prompt Construction | Foundation | AUGMENT | Pi system-prompt.ts |  | extension | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: locus-extension/src/hooks/index.ts. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus-extension/src/hooks/index.ts | declared files missing: locus-extension/src/hooks/index.ts
F-0003 | §1.3: Tool System | Tool System (13 Canonical Tools) | Foundation | AUGMENT | Pi tools/index.ts + Locus | AgentTool | extension | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: locus-extension/src/tools/index.ts. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus-extension/src/tools/index.ts | declared files missing: locus-extension/src/tools/index.ts
F-0004 | §1.4: Model Management | Model Management & Escalation | Foundation | AUGMENT | Pi model-resolver.ts |  | sidecar | NO_EVIDENCE | 0 | 85 | 85 | Files claimed but absent: sidecar/life_os.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/life_os.py | declared files missing: sidecar/life_os.py
F-0005 | §1.5: Extension Lifecycle (25+ Events) | Extension Lifecycle | Foundation | KEEP-PI | Pi agent-session.ts |  | extension | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: locus-extension/index.ts. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus-extension/index.ts | declared files missing: locus-extension/index.ts
F-0006 | §1.6: Context Window Management | Context Window Management | Foundation | AUGMENT | Pi compaction/ + Headroom | CompressionProvider | sidecar | NO_EVIDENCE | 0 | 70 | 70 | Files claimed but absent: sidecar/context/headroom_adapter.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/context/headroom_adapter.py | declared files missing: sidecar/context/headroom_adapter.py
F-0007 | §1.7 + §10.1: Post-Turn Background Review | Post-Turn Review | Foundation | AUGMENT | Hermes background_review.py | PostTurnProvider | sidecar | NO_EVIDENCE | 0 | 80 | 80 | Files claimed but absent: sidecar/learning/reflector.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/learning/reflector.py | declared files missing: sidecar/learning/reflector.py
F-0008 | §1.8: Stream Diagnostics | Stream Diagnostics | Foundation | KEEP-PI | Pi Agent built-in |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/agent/
F-0009 | §1.9: Rate Limit Tracking | Rate Limit Tracking | Foundation | AUGMENT | Pi + Locus |  | sidecar | NO_EVIDENCE | 0 | 80 | 80 | Files claimed but absent: sidecar/rate_limiter.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/rate_limiter.py | declared files missing: sidecar/rate_limiter.py
F-0010 | §1.10: Usage / Cost Tracking | Usage/Cost Tracking | Foundation | AUGMENT | Pi + Locus |  | sidecar | NO_EVIDENCE | 0 | 75 | 75 | Files claimed but absent: sidecar/cost_tracker.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/cost_tracker.py | declared files missing: sidecar/cost_tracker.py
F-0011 | §1.11: Title Generation | Title Generation | Foundation | AUGMENT | Pi + Locus |  | sidecar | NO_EVIDENCE | 0 | 75 | 75 | Files claimed but absent: sidecar/title_generator.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/title_generator.py | declared files missing: sidecar/title_generator.py
F-0012 | §1.12: Onboarding Flow | Onboarding Flow | Foundation | AUGMENT | Pi + Locus CLI |  | sidecar | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: locus_cli/setup.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus_cli/setup.py | declared files missing: locus_cli/setup.py
F-0013 | §1.13: Agent Initialization | Agent Initialization | Foundation | KEEP-PI | Pi Agent |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/agent/
F-0014 | §2.1: 30+ LLM Providers | 30+ LLM Providers | LLM Providers | KEEP-PI | Pi model-registry.ts |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/ai/
F-0015 | §2.2: OAuth Flows | OAuth Flows | LLM Providers | KEEP-PI | Pi Agent |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/ai/
F-0016 | §2.3: Custom / Local Models | Custom/Local Models | LLM Providers | KEEP-PI | Pi Agent |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/ai/
F-0017 | §2.4: Provider Registry | Provider Registry | LLM Providers | KEEP-PI | Pi Agent |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/ai/
F-0018 | §2.5: Model Selection | Model Selection | LLM Providers | KEEP-PI | Pi Agent |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/ai/
F-0019 | §3.1: File Read/Write/Edit; §3.2: Shell / Bash; §3.3: Grep / Search; §3.4: List / Find; §3.5: Web Search; §3.6: Web Fetch | File/Shell/Search Tools | Built-in Tools | KEEP-PI | Pi tools/* |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/coding-agent/src/core/tools/
F-0020 | §3.7 + §11.5: Coding Harness Delegation | Harness Delegation | Built-in Tools | MULTI-PROVIDER | Pi + Hermes + Locus | HarnessProvider | sidecar | NO_EVIDENCE | 0 | 65 | 65 | Files claimed but absent: sidecar/inter_harness_bridge.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/inter_harness_bridge.py | declared files missing: sidecar/inter_harness_bridge.py
F-0021 | §4.1-4.2: Graph-Native Memory (Neo4j Agent Memory) | Neo4j Agent Memory (POLE+O) | Memory | KEEP-PREBUILT | neo4j-labs/agent-memory | MemoryProvider | sidecar | NO_EVIDENCE | 0 | 80 | 80 | Files claimed but absent: sidecar/neo4j_memory.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/neo4j_memory.py | declared files missing: sidecar/neo4j_memory.py
F-0022 | §4.10: Holographic Reduced Representations (HRR Memory Binding) | Holographic HRR | Memory | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 30 | 30 | Files claimed but absent: sidecar/holographic/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/holographic/ | declared files missing: sidecar/holographic/
F-0023 | §4.12: STDP Reinforcement (Spike-Timing-Dependent Plasticity) | STDP Reinforcement | Memory | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 40 | 40 | Files claimed but absent: sidecar/patterns/hebbian.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/patterns/hebbian.py | declared files missing: sidecar/patterns/hebbian.py
F-0024 | §4.13: Spaced Repetition Memory Consolidation (FSRS / SM-2) | Spaced Repetition | Memory | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 60 | 60 | Files claimed but absent: sidecar/spaced_rep.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/spaced_rep.py | declared files missing: sidecar/spaced_rep.py
F-0025 | §4.14: Project-Specific Memory Decay Engine | Project Memory Decay | Memory | LOCUS-NEW | Locus design spec |  | unknown | NO_EVIDENCE | 0 | 25 | 25 | Name the files this feature lives in (evidence.files). | NO_FILES_NAMED, OVERCLAIM |  | no evidence files declared
F-0026 | §4.17: Token Compression (Headroom CCR) | Headroom CCR | Memory | KEEP-PREBUILT | headroomlabs-ai/headroom | CompressionProvider | sidecar | NO_EVIDENCE | 0 | 50 | 50 | Files claimed but absent: sidecar/context/headroom_adapter.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/context/headroom_adapter.py | declared files missing: sidecar/context/headroom_adapter.py
F-0027 | §5.1-5.8: Session Management & Telegram Bridge | Session Management | Sessions | AUGMENT | Pi session-manager.ts + Locus |  | sidecar | NO_EVIDENCE | 0 | 80 | 80 | Files claimed but absent: sidecar/memory.py, sidecar/session_export.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/memory.py, sidecar/session_export.py | declared files missing: sidecar/memory.py, sidecar/session_export.py
F-0028 | §6.2: Dynamic Context References (@file, @symbol, @git, @diff) | Context References | Context | AUGMENT | Pi context-references.ts |  | unknown | NO_EVIDENCE | 0 | 40 | 40 | Name the files this feature lives in (evidence.files). | NO_FILES_NAMED, OVERCLAIM |  | no evidence files declared
F-0029 | §6.3: Coding Context Engine (Repo Map, AST Index, Active Diff) | Coding Context | Context | AUGMENT | Pi coding-context.ts |  | unknown | NO_EVIDENCE | 0 | 90 | 90 | Name the files this feature lives in (evidence.files). | NO_FILES_NAMED, OVERCLAIM |  | no evidence files declared
F-0030 | §7.1-7.9: Terminal Interface & Footer Widget | TUI / Dashboard | Interface | AUGMENT | Pi TUI + Locus dashboard |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: locus_cli/curses_ui.py, sidecar/display/dashboard.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus_cli/curses_ui.py, sidecar/display/dashboard.py | declared files missing: locus_cli/curses_ui.py, sidecar/display/dashboard.py
F-0031 | §8.1-8.10: CLI Commands | CLI / Doctor Diagnostics | CLI | AUGMENT | Pi CLI + Locus CLI |  | sidecar | NO_EVIDENCE | 0 | 85 | 85 | Files claimed but absent: locus_cli/main.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus_cli/main.py | declared files missing: locus_cli/main.py
F-0032 | §9.1: Extension System & Event Lifecycle (25+ Events) | Extension System | Extensions | KEEP-PI | Pi extensions |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/coding-agent/
F-0033 | §9.4: Agent Communication Protocol (ACP Client & Transport) | ACP Protocol | Extensions | LOCUS-NEW | Hermes copilot_acp_client.py |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/acp_server.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/acp_server.py | declared files missing: sidecar/acp_server.py
F-0034 | §9.9: Plugin LLM Sandboxing & Auxiliary Bridge | Plugin LLM | Extensions | LOCUS-NEW | Hermes plugin_llm.py |  | unknown | NO_EVIDENCE | 0 | 10 | 10 | Name the files this feature lives in (evidence.files). | NO_FILES_NAMED |  | no evidence files declared
F-0035 | §1.7 + §10.1: Post-Turn Background Review; §10.3: User Profile Building; §10.5: Personal Reward Model; §10.6-10.7: Hebbian Learning & Pattern Engine | Learning / Profiling / Reward Model | Learning | MULTI-PROVIDER | Hermes + OpenHuman + Locus | LearningProvider | sidecar | NO_EVIDENCE | 0 | 70 | 70 | Files claimed but absent: sidecar/learning/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/learning/ | declared files missing: sidecar/learning/
F-0036 | §3.7 + §11.5: Coding Harness Delegation; §11.1-11.5: Subagent Spawning, Archetypes, Depth Limiting | Subagents / AutoResearch | Subagents | AUGMENT | Pi + OpenHuman + AutoResearch | SubagentArchetype | sidecar | NO_EVIDENCE | 0 | 60 | 60 | Files claimed but absent: sidecar/delegation/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/delegation/ | declared files missing: sidecar/delegation/
F-0037 | §13.1: Prompt Injection Protection | Injection Filter | Security | AUGMENT | Pi + Hermes + Locus |  | sidecar | NO_EVIDENCE | 0 | 80 | 80 | Files claimed but absent: sidecar/security/injection_filter.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/security/injection_filter.py | declared files missing: sidecar/security/injection_filter.py
F-0038 | §13.3: Sandbox Backends | Shell Sandbox | Security | KEEP-PI | Pi trust model | SandboxProvider | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/coding-agent/
F-0039 | §13.6: Project Trust | Project Trust | Security | KEEP-PI | Pi Agent |  | pi | INHERITED_OK | 100 | 100 | 0 |  |  | packages/coding-agent/
F-0040 | §13.7: Shell Blocklist | Shell Blocklist | Security | AUGMENT | Pi + Locus |  | sidecar | NO_EVIDENCE | 0 | 70 | 70 | Files claimed but absent: sidecar/security/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/security/ | declared files missing: sidecar/security/
F-0041 | §13.8: Data Redaction | Data Redaction | Security | AUGMENT | Pi + Locus |  | sidecar | NO_EVIDENCE | 0 | 75 | 75 | Files claimed but absent: sidecar/security/redact.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/security/redact.py | declared files missing: sidecar/security/redact.py
F-0042 | §13.9: Think Token Scrubbing | Think Token Scrubbing | Security | AUGMENT | Pi + Locus |  | sidecar | NO_EVIDENCE | 0 | 75 | 75 | Files claimed but absent: sidecar/security/think_scrubber.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/security/think_scrubber.py | declared files missing: sidecar/security/think_scrubber.py
F-0043 | §13.10: Message Sanitization | Message Sanitization | Security | AUGMENT | Pi + Locus |  | sidecar | NO_EVIDENCE | 0 | 75 | 75 | Files claimed but absent: sidecar/security/sanitizer.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/security/sanitizer.py | declared files missing: sidecar/security/sanitizer.py
F-0044 | §14.1-14.4: Voice Pipeline | STT / TTS Providers | Voice | MULTI-PROVIDER | Hermes + Locus | STTProvider, TTSProvider | sidecar | NO_EVIDENCE | 0 | 60 | 60 | Files claimed but absent: sidecar/voice/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/voice/ | declared files missing: sidecar/voice/
F-0045 | §16.1-16.2 + §20.1-20.3: Browser Automation & Desktop Control | Browser Automation | Browser | MULTI-PROVIDER | OpenHuman + Pi | BrowserProvider | sidecar | NO_EVIDENCE | 0 | 45 | 45 | Files claimed but absent: sidecar/browser/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/browser/ | declared files missing: sidecar/browser/
F-0046 | §17.1-17.11: Channel Adapters & Platform Registry | Telegram Gateway | Gateway | AUGMENT | Hermes + Locus | ChannelProvider | sidecar | NO_EVIDENCE | 0 | 90 | 90 | Files claimed but absent: sidecar/gateway/, gateway/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/gateway/, gateway/ | declared files missing: sidecar/gateway/, gateway/
F-0047 | §17.10: Graceful Gateway Restart & State Snapshotting | Graceful Restart | Gateway | AUGMENT | Hermes + Locus |  | sidecar | NO_EVIDENCE | 0 | 50 | 50 | Files claimed but absent: sidecar/gateway/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/gateway/ | declared files missing: sidecar/gateway/
F-0048 | §18.1-18.4: Model Context Protocol; §18.5: Obsidian MCP (Vault Bridge) | MCP Server/Client | MCP | AUGMENT | OpenHuman + Locus |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/mcp_client.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/mcp_client.py | declared files missing: sidecar/mcp_client.py
F-0049 | §19.2: Trajectory Recording | Trajectory Recording | Observability | AUGMENT | Hermes trajectory_compressor.py |  | sidecar | NO_EVIDENCE | 0 | 40 | 40 | Files claimed but absent: sidecar/learning/trajectory.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/learning/trajectory.py | declared files missing: sidecar/learning/trajectory.py
F-0050 | §19.3: Daily AI Chat Archiver (Multi-Platform Ingestion) | AI Chat Archiver | Observability | LOCUS-NEW | Locus design spec | ChatArchiverProvider | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/ingestion/chat_archiver.py, sidecar/crawlers/chat_crawler.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/ingestion/chat_archiver.py, sidecar/crawlers/chat_crawler.py | declared files missing: sidecar/ingestion/chat_archiver.py, sidecar/crawlers/chat_crawler.py
F-0051 | §16.1-16.2 + §20.1-20.3: Browser Automation & Desktop Control | Computer Use / Screen | Desktop | AUGMENT | OpenHuman + Pi |  | sidecar | NO_EVIDENCE | 0 | 40 | 40 | Files claimed but absent: sidecar/screen/. Create them or correct the path. | CLAIMED_FILES_MISSING, LOW_CONFIDENCE_MAPPING, OVERCLAIM | sidecar/screen/ | declared files missing: sidecar/screen/
F-0052 | §20.3: VNC / Remote Desktop Protocol Control | VNC Remote | Desktop | LOCUS-NEW | Locus design spec |  | unknown | NO_EVIDENCE | 0 | 20 | 20 | Name the files this feature lives in (evidence.files). | NO_FILES_NAMED |  | no evidence files declared
F-0053 | §21.1-21.3: Google Calendar, Gmail, Webhooks | Google Calendar | Integrations | LOCUS-NEW | Locus design spec | IntegrationProvider | sidecar | NO_EVIDENCE | 0 | 35 | 35 | Files claimed but absent: sidecar/integrations/calendar_sync.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/integrations/calendar_sync.py | declared files missing: sidecar/integrations/calendar_sync.py
F-0054 | §23.1-23.5: Tests, Docker, Batch Runner | CI/CD / Docker | Deployment | AUGMENT | Pi + Locus |  | mixed | NO_EVIDENCE | 0 | 65 | 65 | Files claimed but absent: docker-compose.yml, sidecar/deployment/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | docker-compose.yml, sidecar/deployment/ | declared files missing: docker-compose.yml, sidecar/deployment/
F-0055 | §25.1: Four Factions Framework; §25.2: Daily Capacity Score (DCS); §25.3: Five Operating Modes; §25.4: Task Weight Score (TWS) | DCS / TWS / Factions | Life OS | LOCUS-NEW | Locus LOCUS_SYSTEM_v1.md | LifeOSProvider | sidecar | NO_EVIDENCE | 0 | 90 | 90 | Files claimed but absent: sidecar/life_os.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/life_os.py | declared files missing: sidecar/life_os.py
F-0056 | §25.5: Three-Layer Goal Stack; §25.6: Action Gap Tracking; §25.7: Deferral Detection (3/5/8+); §25.8: Lag Score + TWS Lag Bonus | Operating Modes / Scheduler | Life OS | LOCUS-NEW | Locus design spec | SchedulerProvider | sidecar | NO_EVIDENCE | 0 | 85 | 85 | Files claimed but absent: sidecar/life_os.py, sidecar/scheduler/. Create them or correct the path. | CLAIMED_FILES_MISSING, LOW_CONFIDENCE_MAPPING, OVERCLAIM | sidecar/life_os.py, sidecar/scheduler/ | declared files missing: sidecar/life_os.py, sidecar/scheduler/
F-0057 | §25.12: Six-Step Scheduling Algorithm (Full Mathematical Specification) | Goal Tracker (3-Layer Stack) | Life OS | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 85 | 85 | Files claimed but absent: sidecar/life_os.py. Create them or correct the path. | CLAIMED_FILES_MISSING, LOW_CONFIDENCE_MAPPING, OVERCLAIM | sidecar/life_os.py | declared files missing: sidecar/life_os.py
F-0058 | §12.1-12.5 + §26.1: Proactive Inner Loop & Scheduling; §26.1: Inner Loop (Proactive Thinker — 10-Step Execution Pipeline); §26.2: State Engine + Inferred Cause Chain; §26.3: Multi-Horizon Pattern Engine; §26.7: Weekly Full Vault Synthesis | Proactive Inner Loop | Proactive | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 70 | 70 | Files claimed but absent: sidecar/cron_runner.py, sidecar/scheduler/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/cron_runner.py, sidecar/scheduler/ | declared files missing: sidecar/cron_runner.py, sidecar/scheduler/
F-0059 | §27.1: Vectorless Retrieval (PageIndex) | PageIndex Retrieval | Retrieval | KEEP-PREBUILT | VectifyAI/PageIndex | RetrievalProvider | sidecar | NO_EVIDENCE | 0 | 85 | 85 | Files claimed but absent: sidecar/search/pageindex.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/search/pageindex.py | declared files missing: sidecar/search/pageindex.py
F-0060 | §27.2: Obsidian Self-Hosted LiveSync & CouchDB Real-Time Sync Engine | Obsidian Self-Hosted LiveSync & CouchDB Real-Time Sync Engine | Retrieval | AUGMENT | CouchDB 3.3 + vstor/obsidian-livesync protocol | VaultSyncProvider | mixed | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: sidecar/vault/livesync_bridge.py, src/extensions/locus-extension.ts, docker-compose.yml, data/couchdb/local.ini. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/vault/livesync_bridge.py, src/extensions/locus-extension.ts, docker-compose.yml, data/couchdb/local.ini | declared files missing: sidecar/vault/livesync_bridge.py, src/extensions/locus-extension.ts, docker-compose.yml, data/couchdb/local.ini
F-0061 | §27.5: Rough Note Parser & Idea Tracker | Rough Note Parser | Retrieval | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 75 | 75 | Files claimed but absent: sidecar/ingestion/rough_note_parser.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/ingestion/rough_note_parser.py | declared files missing: sidecar/ingestion/rough_note_parser.py
F-0062 | §27.6: Link Dump & Web Resource Logger | Link Dump Logger | Retrieval | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 75 | 75 | Files claimed but absent: sidecar/ingestion/link_logger.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/ingestion/link_logger.py | declared files missing: sidecar/ingestion/link_logger.py
F-0063 | §27.7: Excalidraw MCP Skill (Visual Architecture Diagrams) | Excalidraw MCP Skill | Retrieval | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 70 | 70 | Files claimed but absent: sidecar/display/excalidraw_builder.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/display/excalidraw_builder.py | declared files missing: sidecar/display/excalidraw_builder.py
F-0064 | §28.1-28.6: Dual-Interface, Check-ins, Voice, Cost Model | Dual Interface / Check-ins | Interface | LOCUS-NEW | Locus design spec |  | mixed | NO_EVIDENCE | 0 | 85 | 85 | Files claimed but absent: sidecar/gateway/, locus-extension/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/gateway/, locus-extension/ | declared files missing: sidecar/gateway/, locus-extension/
F-0065 | §29.1: Error Classifier | Error Classifier | Observability | AUGMENT | Hermes error_classifier.py |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/diagnostics/error_classifier.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/diagnostics/error_classifier.py | declared files missing: sidecar/diagnostics/error_classifier.py
F-0066 | §29.3: Health Checks | Health Checks | Observability | AUGMENT | Hermes + OpenHuman |  | sidecar | NO_EVIDENCE | 0 | 90 | 90 | Files claimed but absent: locus_cli/main.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus_cli/main.py | declared files missing: locus_cli/main.py
F-0067 | §29.4: Notifications | Notifications | Observability | AUGMENT | Locus |  | sidecar | NO_EVIDENCE | 0 | 65 | 65 | Files claimed but absent: sidecar/gateway/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/gateway/ | declared files missing: sidecar/gateway/
F-0068 | §29.5: Connectivity Check | Connectivity Check | Observability | AUGMENT | Locus |  | unknown | NO_EVIDENCE | 0 | 60 | 60 | Name the files this feature lives in (evidence.files). | NO_FILES_NAMED, OVERCLAIM |  | no evidence files declared
F-0069 | §29.6: Code Graph Analysis | Code Graph | Observability | AUGMENT | Locus |  | infra | NO_EVIDENCE | 0 | 50 | 50 | Files claimed but absent: .graphifyignore. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | .graphifyignore | declared files missing: .graphifyignore
F-0070 | §29.7: Subconscious Background Processing | Subconscious | Observability | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 40 | 40 | Files claimed but absent: sidecar/heartbeat/. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/heartbeat/ | declared files missing: sidecar/heartbeat/
F-0071 | §29.8: Workflows | Workflows | Observability | LOCUS-NEW | Locus design spec |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/scheduler/workflow.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/scheduler/workflow.py | declared files missing: sidecar/scheduler/workflow.py
F-0072 | §30.1: Collector + Chunker (Ingestion Pipeline) | Collector + Chunker | Microsystems | LOCUS-NEW | Locus microsystems.html |  | sidecar | NO_EVIDENCE | 0 | 60 | 60 | Files claimed but absent: sidecar/ingestion/collector.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/ingestion/collector.py | declared files missing: sidecar/ingestion/collector.py
F-0073 | §30.2: Cause Chain Engine (Inferred Causation) | Cause Chain Engine | Microsystems | LOCUS-NEW | Locus comprehensive_design.html |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/cause_chain.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/cause_chain.py | declared files missing: sidecar/cause_chain.py
F-0074 | §30.3: SOUL.md / Wants Engine (Personality Layer) | SOUL.md / Wants Engine | Microsystems | LOCUS-NEW | Locus comprehensive_design.html |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/soul.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/soul.py | declared files missing: sidecar/soul.py
F-0075 | §30.4: Content Engine (8-Step Social & Thought Publication Pipeline) | Content Engine | Microsystems | LOCUS-NEW | Locus microsystems.html |  | sidecar | NO_EVIDENCE | 0 | 60 | 60 | Files claimed but absent: sidecar/content/engine.py. Create them or correct the path. | CLAIMED_FILES_MISSING, LOW_CONFIDENCE_MAPPING, OVERCLAIM | sidecar/content/engine.py | declared files missing: sidecar/content/engine.py
F-0076 | §30.5: Spaced Repetition Engine | Spaced Repetition | Microsystems | LOCUS-NEW | Locus microsystems.html |  | sidecar | NO_EVIDENCE | 0 | 60 | 60 | Files claimed but absent: sidecar/spaced_rep.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/spaced_rep.py | declared files missing: sidecar/spaced_rep.py
F-0077 | §30.6: QLoRA Fine-Tuning Pipeline | QLoRA Pipeline | Microsystems | LOCUS-NEW | Locus pyramid.html |  | sidecar | NO_EVIDENCE | 0 | 25 | 25 | Files claimed but absent: sidecar/evolution/dataset_curator.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/evolution/dataset_curator.py | declared files missing: sidecar/evolution/dataset_curator.py
F-0078 | §30.7: Master Conductor (11-Step Ingress-to-Egress Pipeline) | Master Conductor | Microsystems | LOCUS-NEW | Locus microsystems.html |  | sidecar | NO_EVIDENCE | 0 | 90 | 90 | Files claimed but absent: sidecar/conductor.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/conductor.py | declared files missing: sidecar/conductor.py
F-0079 | §30.8: Real-Time Dashboard & TUI Specification (6-Step Architecture) | Dashboard/TUI Spec | Microsystems | LOCUS-NEW | Locus microsystems.html |  | sidecar | NO_EVIDENCE | 0 | 45 | 45 | Files claimed but absent: locus_cli/curses_ui.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | locus_cli/curses_ui.py | declared files missing: locus_cli/curses_ui.py
F-0080 | §30.9: Redis High-Performance State & Pub/Sub Integration | Redis Integration | Microsystems | LOCUS-NEW | Locus microsystems.html |  | sidecar | NO_EVIDENCE | 0 | 55 | 55 | Files claimed but absent: sidecar/redis_state.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/redis_state.py | declared files missing: sidecar/redis_state.py
F-0081 | §30.10: Obsidian & LightRAG Dual-Index Knowledge Bridge | Obsidian/LightRAG Bridge | Microsystems | LOCUS-NEW | Locus microsystems.html |  | sidecar | NO_EVIDENCE | 0 | 45 | 45 | Files claimed but absent: sidecar/vault/lightrag_bridge.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/vault/lightrag_bridge.py | declared files missing: sidecar/vault/lightrag_bridge.py
F-0082 | (not a spec section) | Install Script (ALL platforms) | Infrastructure | LOCUS-NEW | Locus design |  | unknown | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: install.ps1, install.sh, install.bat, locus.bat .... Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | install.ps1, install.sh, install.bat, locus.bat, locus.cmd | declared files missing: install.ps1, install.sh, install.bat, locus.bat, locus.cmd
F-0083 | (not a spec section) | Telegram Setup via /setup command | Infrastructure | LOCUS-NEW | Locus design |  | unknown | NO_EVIDENCE | 0 | 100 | 100 | Name the files this feature lives in (evidence.files). | NO_FILES_NAMED, OVERCLAIM |  | no evidence files declared
F-0084 | (not a spec section) | core/ vs sidecar/ Deduplication | Infrastructure | UNKNOWN | Internal cleanup |  | sidecar | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: sidecar/, sidecar/__init__.py. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | sidecar/, sidecar/__init__.py | declared files missing: sidecar/, sidecar/__init__.py
F-0085 | (not a spec section) | VM Backend Setup | Infrastructure | LOCUS-NEW | Locus design |  | infra | NO_EVIDENCE | 0 | 100 | 100 | Files claimed but absent: HEADLESS_VM_AND_CRON_SETUP_GUIDE.md, install.sh, install.ps1, docker-compose.yml. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | HEADLESS_VM_AND_CRON_SETUP_GUIDE.md, install.sh, install.ps1, docker-compose.yml | declared files missing: HEADLESS_VM_AND_CRON_SETUP_GUIDE.md, install.sh, install.ps1, docker-compose.yml
F-0086 | (not a spec section) | Deployment (systemd/Docker) | Infrastructure | AUGMENT | Locus design |  | infra | NO_EVIDENCE | 0 | 65 | 65 | Files claimed but absent: docker-compose.yml. Create them or correct the path. | CLAIMED_FILES_MISSING, OVERCLAIM | docker-compose.yml | declared files missing: docker-compose.yml
F-0087 | (not a spec section) | ARCH-6 Pi bridge (sidecar -> Pi CLI, used by cron + Telegram + conductor) | Infrastructure | LOCUS-NEW | Locus-original |  | sidecar | NO_EVIDENCE | 0 |  |  | Files claimed but absent: sidecar/pi_bridge.py, sidecar/cron_runner.py. Create them or correct the path. | CLAIMED_FILES_MISSING | sidecar/pi_bridge.py, sidecar/cron_runner.py | declared files missing: sidecar/pi_bridge.py, sidecar/cron_runner.py
F-0088 | §4.5: Memory Tree (Hierarchical Summarization Cascade) | Memory Tree (Hierarchical Summarization Cascade) |  | AUGMENT |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0089 | §4.7: Memory Sync (Multi-Source Ingestion Pipelines) | Memory Sync (Multi-Source Ingestion Pipelines) |  | AUGMENT |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0090 | §4.8: Memory Queue (Async Job Pipeline) | Memory Queue (Async Job Pipeline) |  | AUGMENT |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0091 | §4.9: Memory Diff (Snapshot-Based Change Tracking) | Memory Diff (Snapshot-Based Change Tracking) |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0092 | §2.1-2.3: Query Router / Intent Classifier (Stage 2) | Query Router / Intent Classifier (Stage 2) |  | UNKNOWN |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0093 | §2.4: State Engine (Stage 3) | State Engine (Stage 3) |  | UNKNOWN |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0094 | §2.5: Context Forge (Stage 6) — The 6-Layer Assembler | Context Forge (Stage 6) — The 6-Layer Assembler |  | UNKNOWN |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0095 | §2.6: Anti-Hallucination Guard (Stage 10) | Anti-Hallucination Guard (Stage 10) |  | UNKNOWN |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0096 | §2.7-2.8: Intelligent Model Routing + Quality-Based Fallback | Intelligent Model Routing + Quality-Based Fallback |  | AUGMENT |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0097 | §2.6a: Streaming (SSE) | Streaming (SSE) |  | KEEP-PI |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0098 | §2.9: Image Generation | Image Generation |  | KEEP-PI |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0099 | §3.7a: Git Tools | Git Tools |  | AUGMENT |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0100 | §3.8: Tool Call Validation | Tool Call Validation |  | AUGMENT |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0101 | §3.9: Tool Result Classification | Tool Result Classification |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0102 | §3.10: Tool Output Accumulator | Tool Output Accumulator |  | KEEP-PI |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0103 | §3.11: Tool Timeout / Budget | Tool Timeout / Budget |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0104 | §3.12: Custom Locus Tools | Custom Locus Tools |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0105 | §15.1: Web Search (8 Providers) | Web Search (8 Providers) |  | KEEP-PI |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0106 | §24.1: Pi Utilities (Clipboard, Syntax Highlighting, Frontmatter, File Watcher) | Pi Utilities (Clipboard, Syntax Highlighting, Frontmatter, File Watcher) |  | KEEP-PI |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0107 | §13.2: File Safety | File Safety |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0108 | §13.4: Autonomy Tiers | Autonomy Tiers |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0109 | §13.5: Approval Gate | Approval Gate |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0110 | §4.16: Context Compression | Context Compression |  | UNKNOWN |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0111 | §25.9: Emergency Task Injection | Emergency Task Injection |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0112 | §25.10: Exhaustion Predictor | Exhaustion Predictor |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0113 | §25.11: Weekly Faction Rebalance | Weekly Faction Rebalance |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0114 | §25.13: Review Cadence System | Review Cadence System |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0115 | §25.14: Goal Stack Enforcement | Goal Stack Enforcement |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0116 | §25.15: Cross-Faction Efficiency | Cross-Faction Efficiency |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0117 | §25.16: Four-Level Emergency Protocol | Four-Level Emergency Protocol |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0118 | §4.18: Memory Provider Interface | Memory Provider Interface |  | UNKNOWN |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0119 | §9.2: Skill System & Multi-Source Marketplace | Skill System & Multi-Source Marketplace |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0120 | §10.8: Self-Evolving Architect Bot | Self-Evolving Architect Bot |  | UNKNOWN |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0121 | §10.9: Agent Experience Tracking (Procedural Memory) | Agent Experience Tracking (Procedural Memory) |  | MULTI-PROVIDER |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0122 | §27.3: LOCUS_SHORTHAND 4× Text Compressor | LOCUS_SHORTHAND 4× Text Compressor |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0123 | §27.4: 3-Level Tag Hierarchy & Semantic Indexing | 3-Level Tag Hierarchy & Semantic Indexing |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0124 | §29.2: Auxiliary LLM Client | Auxiliary LLM Client |  | LOCUS-NEW |  |  | unknown | NO_EVIDENCE | 0 |  |  | Name the files this feature lives in (evidence.files). |  |  | no evidence files declared
F-0125 | (not a spec section) | Modularity foundation: provider registry + config accessor (sidecar and TypeScript) | Infrastructure | LOCUS-NEW | Locus-original |  | mixed | NO_EVIDENCE | 0 |  |  | Files claimed but absent: sidecar/registry.py, sidecar/config.py, locus-extension/src/registry.ts, locus-extension/src/config.ts. Create them or correct the path. | CLAIMED_FILES_MISSING | sidecar/registry.py, sidecar/config.py, locus-extension/src/registry.ts, locus-extension/src/config.ts | declared files missing: sidecar/registry.py, sidecar/config.py, locus-extension/src/registry.ts, locus-extension/src/config.ts

## Summary
GENERATED FROM EVIDENCE. Do not edit.
Generated at | 2026-10-14T17:01:43+0530
Commit | 4c0b14e7a05245b322cdc0c60b086200a73799af (dirty)
Guard verdict | FAIL
Features tracked
Verified average %
OLD claimed average % (unverified, from the previous tracker)
Features the old tracker claimed >= 25 points above evidence
Integrated or better (>= 85%)
Level NO_EVIDENCE
Level FILES_PRESENT
Level IMPLEMENTED
Level UNIT_VERIFIED
Level INTEGRATED
Level PROVEN
Level INHERITED_OK
Spec sections in the spec file | 135

## Legend
Level | Meaning (a level needs every level below it) | %
NO_EVIDENCE | Nothing declared, or declared files are missing | 0
FILES_PRESENT | Every declared file exists and is non-empty | 15
IMPLEMENTED | Declared functions/classes exist and are not stubs | 40
UNIT_VERIFIED | Declared unit commands / guard checks pass; tests have real assertions | 65
INTEGRATED | Integration test through the Pi path passes | 85
PROVEN | Recorded end-to-end proof is current AND a human signed off | 100
INHERITED_OK | KEEP-PI feature: file present and packages/ matches the pinned upstream | 100
Rule | Nobody types a status. tracker/features.yaml holds evidence; tools/tracker/verify.py computes; this file is regenerated.

## Spec Coverage
Spec line | Spec section | Feature ids | Mapping
211 | §1.1: Pi Agent Loop (Foundation) | F-0001 | exact
355 | §1.2: System Prompt Construction | F-0002 | exact
419 | §1.3: Tool System | F-0003 | exact
471 | §1.4: Model Management | F-0004 | exact
506 | §1.5: Extension Lifecycle (25+ Events) | F-0005 | exact
551 | §1.6: Context Window Management | F-0006 | exact
586 | §4.1-4.2: Graph-Native Memory (Neo4j Agent Memory) | F-0021 | grouped
653 | §4.17: Token Compression (Headroom CCR) | F-0026 | exact
716 | §4.5: Memory Tree (Hierarchical Summarization Cascade) | F-0088 | exact
824 | §4.7: Memory Sync (Multi-Source Ingestion Pipelines) | F-0089 | exact
925 | §4.8: Memory Queue (Async Job Pipeline) | F-0090 | exact
1031 | §4.9: Memory Diff (Snapshot-Based Change Tracking) | F-0091 | exact
1166 | §4.10: Holographic Reduced Representations (HRR Memory Binding) | F-0022 | exact
1247 | §4.12: STDP Reinforcement (Spike-Timing-Dependent Plasticity) | F-0023 | exact
1327 | §4.13: Spaced Repetition Memory Consolidation (FSRS / SM-2) | F-0024 | exact
1412 | §4.14: Project-Specific Memory Decay Engine | F-0025 | exact
1477 | §27.1: Vectorless Retrieval (PageIndex) | F-0059 | exact
1598 | §2.1-2.3: Query Router / Intent Classifier (Stage 2) | F-0092 | exact
1704 | §2.4: State Engine (Stage 3) | F-0093 | exact
1752 | §2.5: Context Forge (Stage 6) — The 6-Layer Assembler | F-0094 | exact
1812 | §2.6: Anti-Hallucination Guard (Stage 10) | F-0095 | exact
1859 | §2.7-2.8: Intelligent Model Routing + Quality-Based Fallback | F-0096 | exact
2022 | §6.2: Dynamic Context References (@file, @symbol, @git, @diff) | F-0028 | exact
2118 | §6.3: Coding Context Engine (Repo Map, AST Index, Active Diff) | F-0029 | exact
2196 | §1.8: Stream Diagnostics | F-0008 | exact
2200 | §1.9: Rate Limit Tracking | F-0009 | exact
2277 | §1.10: Usage / Cost Tracking | F-0010 | exact
2368 | §1.11: Title Generation | F-0011 | exact
2435 | §1.12: Onboarding Flow | F-0012 | exact
2439 | §1.13: Agent Initialization | F-0013 | exact
2445 | §2.1: 30+ LLM Providers | F-0014 | exact
2450 | §2.2: OAuth Flows | F-0015 | exact
2455 | §2.3: Custom / Local Models | F-0016 | exact
2460 | §2.4: Provider Registry | F-0017 | exact
2465 | §2.5: Model Selection | F-0018 | exact
2470 | §2.6a: Streaming (SSE) | F-0097 | exact
2475 | §2.9: Image Generation | F-0098 | exact
2482 | §3.1: File Read/Write/Edit | F-0019 | grouped
2486 | §3.2: Shell / Bash | F-0019 | grouped
2490 | §3.3: Grep / Search | F-0019 | grouped
2495 | §3.4: List / Find | F-0019 | grouped
2499 | §3.5: Web Search | F-0019 | grouped
2504 | §3.6: Web Fetch | F-0019 | grouped
2509 | §3.7a: Git Tools | F-0099 | exact
2514 | §3.8: Tool Call Validation | F-0100 | exact
2519 | §3.9: Tool Result Classification | F-0101 | exact
2524 | §3.10: Tool Output Accumulator | F-0102 | exact
2529 | §3.11: Tool Timeout / Budget | F-0103 | exact
2533 | §3.12: Custom Locus Tools | F-0104 | exact
2540 | §15.1: Web Search (8 Providers) | F-0105 | exact
2547 | §24.1: Pi Utilities (Clipboard, Syntax Highlighting, Frontmatter, File Watcher) | F-0106 | exact
2556 | §3.7 + §11.5: Coding Harness Delegation | F-0020, F-0036 | grouped
2664 | §1.7 + §10.1: Post-Turn Background Review | F-0007, F-0035 | grouped
2734 | §10.3: User Profile Building | F-0035 | grouped
2833 | §13.1: Prompt Injection Protection | F-0037 | exact
2968 | §13.2: File Safety | F-0107 | exact
2993 | §13.3: Sandbox Backends | F-0038 | exact
3135 | §13.4: Autonomy Tiers | F-0108 | exact
3160 | §13.5: Approval Gate | F-0109 | exact
3193 | §13.6: Project Trust | F-0039 | exact
3201 | §13.7: Shell Blocklist | F-0040 | exact
3265 | §13.8: Data Redaction | F-0041 | exact
3340 | §13.9: Think Token Scrubbing | F-0042 | exact
3426 | §13.10: Message Sanitization | F-0043 | exact
3498 | §17.1-17.11: Channel Adapters & Platform Registry | F-0046 | exact
3682 | §17.10: Graceful Gateway Restart & State Snapshotting | F-0047 | exact
3756 | §4.16: Context Compression | F-0110 | exact
3860 | §18.1-18.4: Model Context Protocol | F-0048 | grouped
4153 | §18.5: Obsidian MCP (Vault Bridge) | F-0048 | grouped
4217 | §12.1-12.5 + §26.1: Proactive Inner Loop & Scheduling | F-0058 | grouped
4317 | §14.1-14.4: Voice Pipeline | F-0044 | grouped
4384 | §25.1: Four Factions Framework | F-0055 | grouped
4410 | §25.2: Daily Capacity Score (DCS) | F-0055 | grouped
4433 | §25.3: Five Operating Modes | F-0055 | grouped
4455 | §25.4: Task Weight Score (TWS) | F-0055 | grouped
4482 | §25.5: Three-Layer Goal Stack | F-0056 | low-confidence
4506 | §25.6: Action Gap Tracking | F-0056 | low-confidence
4525 | §25.7: Deferral Detection (3/5/8+) | F-0056 | low-confidence
4546 | §25.8: Lag Score + TWS Lag Bonus | F-0056 | low-confidence
4567 | §25.9: Emergency Task Injection | F-0111 | exact
4586 | §25.10: Exhaustion Predictor | F-0112 | exact
4605 | §25.11: Weekly Faction Rebalance | F-0113 | exact
4628 | §25.12: Six-Step Scheduling Algorithm (Full Mathematical Specification) | F-0057 | low-confidence
4710 | §25.13: Review Cadence System | F-0114 | exact
4724 | §25.14: Goal Stack Enforcement | F-0115 | exact
4737 | §25.15: Cross-Faction Efficiency | F-0116 | exact
4750 | §25.16: Four-Level Emergency Protocol | F-0117 | exact
4768 | §26.1: Inner Loop (Proactive Thinker — 10-Step Execution Pipeline) | F-0058 | grouped
4837 | §26.2: State Engine + Inferred Cause Chain | F-0058 | grouped
4901 | §26.3: Multi-Horizon Pattern Engine | F-0058 | grouped
4950 | §26.7: Weekly Full Vault Synthesis | F-0058 | grouped
5066 | §4.18: Memory Provider Interface | F-0118 | exact
5141 | §19.2: Trajectory Recording | F-0049 | exact
5200 | §19.3: Daily AI Chat Archiver (Multi-Platform Ingestion) | F-0050 | exact
5266 | §8.1-8.10: CLI Commands | F-0031 | grouped
5388 | §5.1-5.8: Session Management & Telegram Bridge | F-0027 | grouped
5463 | §7.1-7.9: Terminal Interface & Footer Widget | F-0030 | grouped
5531 | §9.1: Extension System & Event Lifecycle (25+ Events) | F-0032 | exact
5572 | §9.2: Skill System & Multi-Source Marketplace | F-0119 | exact
5629 | §9.4: Agent Communication Protocol (ACP Client & Transport) | F-0033 | exact
5715 | §9.9: Plugin LLM Sandboxing & Auxiliary Bridge | F-0034 | exact
5774 | §10.5: Personal Reward Model | F-0035 | grouped
5824 | §10.6-10.7: Hebbian Learning & Pattern Engine | F-0035 | grouped
5878 | §10.8: Self-Evolving Architect Bot | F-0120 | exact
5928 | §10.9: Agent Experience Tracking (Procedural Memory) | F-0121 | exact
6005 | §11.1-11.5: Subagent Spawning, Archetypes, Depth Limiting | F-0036 | grouped
6068 | §16.1-16.2 + §20.1-20.3: Browser Automation & Desktop Control | F-0045, F-0051 | low-confidence
6127 | §20.3: VNC / Remote Desktop Protocol Control | F-0052 | exact
6196 | §21.1-21.3: Google Calendar, Gmail, Webhooks | F-0053 | exact
6253 | §27.2: Obsidian Self-Hosted LiveSync & CouchDB Real-Time Sync Engine | F-0060 | exact
6687 | §27.3: LOCUS_SHORTHAND 4× Text Compressor | F-0122 | exact
6724 | §27.4: 3-Level Tag Hierarchy & Semantic Indexing | F-0123 | exact
6764 | §27.5: Rough Note Parser & Idea Tracker | F-0061 | exact
6826 | §27.6: Link Dump & Web Resource Logger | F-0062 | exact
6877 | §27.7: Excalidraw MCP Skill (Visual Architecture Diagrams) | F-0063 | exact
6953 | §28.1-28.6: Dual-Interface, Check-ins, Voice, Cost Model | F-0064 | grouped
7007 | §29.1: Error Classifier | F-0065 | exact
7044 | §29.2: Auxiliary LLM Client | F-0124 | exact
7073 | §29.3: Health Checks | F-0066 | exact
7103 | §29.4: Notifications | F-0067 | exact
7185 | §29.5: Connectivity Check | F-0068 | exact
7244 | §29.6: Code Graph Analysis | F-0069 | exact
7318 | §29.7: Subconscious Background Processing | F-0070 | exact
7402 | §29.8: Workflows | F-0071 | exact
7527 | §30.1: Collector + Chunker (Ingestion Pipeline) | F-0072 | exact
7580 | §30.2: Cause Chain Engine (Inferred Causation) | F-0073 | exact
7619 | §30.3: SOUL.md / Wants Engine (Personality Layer) | F-0074 | exact
7651 | §30.4: Content Engine (8-Step Social & Thought Publication Pipeline) | F-0075 | low-confidence
7721 | §30.5: Spaced Repetition Engine | F-0076 | exact
7750 | §30.6: QLoRA Fine-Tuning Pipeline | F-0077 | exact
7783 | §30.7: Master Conductor (11-Step Ingress-to-Egress Pipeline) | F-0078 | exact
7861 | §30.8: Real-Time Dashboard & TUI Specification (6-Step Architecture) | F-0079 | exact
7914 | §30.9: Redis High-Performance State & Pub/Sub Integration | F-0080 | exact
7960 | §30.10: Obsidian & LightRAG Dual-Index Knowledge Bridge | F-0081 | exact
8012 | §23.1-23.5: Tests, Docker, Batch Runner | F-0054 | grouped

## _meta (hidden)
grid_sha | 9bfdb2ad105f0d2eaea412c547b56ac0ff937045d72305b9607f584acecb8161
status_sha | 5acf3d8f6492ab2b28fbc1c9953ab285f441b210a81022f0f4e7b124df212e07
commit | 4c0b14e7a05245b322cdc0c60b086200a73799af
generated_at | 2026-10-14T17:01:43+0530
note | generated by tools/tracker/export_xlsx.py - hand edits are detected